Phase 4

Project Planning Phase

## Project Planning Template (Product Backlog, Sprint Planning, Stories, Story Points)

| Field | Value |
| --- | --- |
| Date | 15 February 2026 |
| Team ID | SWTID-2026-1543 |
| Project Name | Virtual Agent–Driven SLA Breach Awareness & Justification System |
| Maximum Marks | 5 Marks |

### Product Backlog, Sprint Schedule, and Estimation

| Sprint | Functional Requirement (Epic) | User Story No. | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | SLA Risk Detection | USN-1 | Configure SLA thresholds so the system flags at-risk tasks automatically | 3 | High | [Team] |
| Sprint-1 | SLA Risk Detection | USN-2 | Build Flow Designer subflow to monitor SLA % elapsed | 5 | High | [Team] |
| Sprint-1 | Notifications | USN-3 | Send real-time notification to assignee on threshold breach | 2 | High | [Team] |
| Sprint-2 | Virtual Agent Governance | USN-4 | Design VA conversation to acknowledge SLA risk and log response | 5 | High | [Team] |
| Sprint-2 | Breach Justification | USN-5 | Enforce mandatory justification field via UI Policy before closure | 3 | High | [Team] |
| Sprint-2 | Breach Justification | USN-6 | Auto-log justification text to work notes | 2 | Medium | [Team] |
| Sprint-3 | Access Control | USN-7 | Restrict SLA field updates to authorized (assignee) role only via ACL | 3 | High | [Team] |
| Sprint-3 | Reporting & Dashboard | USN-8 | Build executive dashboard for SLA trend and breach-rate | 5 | Medium | [Team] |
| Sprint-3 | Reporting & Dashboard | USN-9 | Build accountability report by assignee/team | 3 | Medium | [Team] |

### Project Tracker, Velocity & Burndown Chart

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 10 | 6 Days | [Insert] | [Insert] | [Insert] | [Insert] |
| Sprint-2 | 10 | 6 Days | [Insert] | [Insert] | [Insert] | [Insert] |
| Sprint-3 | 11 | 6 Days | [Insert] | [Insert] | [Insert] | [Insert] |

### Velocity Calculation

Velocity = Total Story Points Completed / Number of Sprints.

Planned total story points across all sprints = 10 + 10 + 11 = 31 across 3 sprints, giving a planned velocity of approximately 10.3 story points per sprint. Update this section with actual completed story points once each sprint closes to calculate real velocity.

### Burndown Chart

Insert the burndown chart (work remaining vs. time) once actual sprint execution data is available from the team's tracking tool (e.g., ServiceNow Agile Development / JIRA).

### Team Roles & Responsibilities

| Role | Responsibility |
| --- | --- |
| Team Lead / Scrum Master | Sprint planning, backlog grooming, removing blockers, stakeholder communication |
| ServiceNow Developer / Admin (Flow Designer) | Builds the SLA Risk Monitor flow, UI Policies, and ACLs |
| Virtual Agent Designer | Designs and builds the guided-conversation topic and NLU intents |
| QA / Tester | Executes functional and performance test cases, logs and tracks defects |
| Reporting Owner | Builds and validates the Performance Analytics dashboard and reports |

### Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Alert fatigue from poorly tuned thresholds | Medium | Medium | Pilot with one team first; tune threshold based on feedback before wider rollout |
| ACL misconfiguration blocking legitimate updates | Low | High | Test ACL rules thoroughly in Sprint 3 against all three roles before go-live |
| Virtual Agent conversation drop-off (agents ignore VA) | Medium | Medium | Keep the conversation short (2–3 steps); reinforce with a follow-up notification if unacknowledged |
| Scope creep into custom scripting | Low | Medium | Maintain a strict zero-code review checkpoint at the end of each sprint |